## Product DSM
PRODUCT DESIGN STRUCTURE MATRIX (DSM) — WITH INTERFACE TYPES
Cell notation = dependency strength · interface type. M = Mechanical · En = Energy · I = Information · Mat = Material
# | PRODUCT | E1 | E2 | E3 | E4 | E5 | E6 | E7 | E8 | E9 | E10 | E11
E1 | Microcontroller (MCU-X) | *
E2 | Programming connector | 1·En/I | *
E3 | Existing & new test points | 3·En/I |  | *
E4 | DUT firmware | 3·I |  |  | *
E5 | FTM Measurement & Signal Conditioning Instrumentation |  |  | 2-E |  | * |  | 1-M | 2-E | 1-I | 2-I
E6 | FTM-to-DUT Programming Interface | 3-I | 3-MEI | 1-MEI | 1-I |  | * |  | 1-M | 2-I
E7 | FTM Fixture / Mechanical Interface |  | 2-MEI | 3-MEI |  | 1-MEI |  | * | 2-MEI
E8 | FTM Electrical Test Interface | 2-I | 1-MEI | 3-MEI |  | 2-E | 1-MEI | 1-M | * | 2-I | 2-I | 1-I
E9 | FTM Fw & Test sequence | 2-I | 1-I | 2-I | 3-I | 3-I | 3-I |  | 2-I | * | 3-I | 1-I
E10 | FTM Test Configuration |  |  |  | 2-I | 1-I |  | 2-I | 3-I |  | * | 1-I
E11 | FTM Technical documentation |  |  |  |  | 3-I | 3-I | 3-I | 3-I | 2-I | 2-I | *
LEGEND
Dependency strength | Meaning |  | Interface code | Interface type | Definition
1 | Weak — informational / low-risk dependency |  | M | Mechanical | Geometry, fit, contact, alignment, mounting or physical constraint
2 | Medium — functional dependency requiring coordination |  | En | Energy | Electrical power / voltage / current transfer
3 | Strong — structural / physical / constraining dependency |  | I | Information | Signals, data, control, firmware/software or documentation
* | Diagonal — element itself |  | Mat | Material | Transfer or flow of physical material; not materially present in this system
|  |  | M/En/I etc. | Mixed interface | More than one interface type acts across the same dependency
Element | Meaning
FTM Measurement & Signal Conditioning Instrumentation | Electronic instruments (power supplies, DMMs, oscilloscopes, DAQ boards) and associated signal conditioning circuits used to generate stimuli and acquire electrical quantities from the DUT
FTM-to-DUT Programming Interface | Dedicated HW/SW channel (e.g. JTAG, SWD, bootloader) for loading firmware/calibrations onto the DUT during the test cycle
FTM Fixture / Mechanical Interface | Mechanical tooling (bed-of-nails, pressers, alignment guides) that positions, holds, and brings the DUT into contact with the bench, ensuring repeatable alignment and contact
FTM Electrical Test Interface | Set of electrical nodes (test points, connectors, pogo pins) through which the bench accesses the DUT's signals for stimulus/measurement, defined by the board's test point map
FTM fw & test sequence | Embedded real-time software and application logic that together drive the bench HW (instrumentation, relays, actuators), manage low-level communication with the DUT, and define the test execution flow — including test order, acceptance limits, pass/fail handling, and generation of test logs/reports.
FTM Test Configuration | Set of parameters, limits, calibration values, and operational settings that define how the FTM firmware & test sequence must execute for a specific board variant — including acceptance thresholds, instrument setpoints, and variant-specific selections (e.g. board revision, backward-compatibility mode).
FTM Technical documentation | Collection of schematics, drawings, procedures, and reference records that describe the FTM's design and configured state, supporting maintainability, traceability, and knowledge transfer over the bench's lifecycle (e.g. wiring diagrams, fixture drawings, calibration procedures, revision history).

## Process DSM
PROCESS-BASED DESIGN STRUCTURE MATRIX (DSM)
Row = dependent activity · Column = activity on which it depends · Duration in weeks
# | Code | Process activity | Duration (weeks) | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
1 | P1 | Requirements / change analysis | 1 | bar: P1
2 | P2 | FTM Impact assessment | 1 | P1: 3; P2: •
3 | P3 | Test strategy definition/review | 1 | P2: 3; P3: •; P11: 2
4 | P4 | FTM Hw design | 3 | P2: 1; P3: 2; P4: •; P10: 2; P11: 2
5 | P5 | FTM FW/ test sequence development | 3 | P3: 3; P4: 2; P5: •; P10: 2; P11: 3
6 | P6 | Mechanical fixture design | 3 | P2: 2; P3: 2; P4: 1; P6: •; P9: 2; P11: 1
7 | P7 | Component procurement* |  | P4: 2; P6: 2; P7: •
8 | P8 | Test machine / fixture manufacturing | 4 | P2: 2; P7: 3; P8: •
9 | P9 | FTM Hw/Mechanical Assembly | 2 | P4: 1; P6: 1; P7: 2; P8: 3; P9: •
10 | P10 | FTM Hw-Sw Implementation | 2 | P4: 1; P5: 3; P10: •
11 | P11 | Internal validation | 3 | P8: 2; P9: 3; P10: 3; P11: •
12 | P12 | Factory Acceptance Test (FAT) & Release | 2 | P11: 3; P12: •
Total nominal process duration |  |  | 25 | P2: *Note: Component procurement is carried out concurrently with HW, FW, and mechanical fixture design
LEGEND
Symbol / value | Meaning | Interpretation
• | Diagonal | Activity itself
1 | Weak dependency | Informational; low coordination / low risk
2 | Medium dependency | Functional; requires coordination
3 | Strong dependency | Structural / physical / constraining
Bold + red fill | Feedback marker | Dependency on a later activity; potential iteration / rework loop
| Activity itself | Meaning
| Requirements / change analysis | Analysis of ECN requirements/impacts on the board
| FTM Impact assessment | Assessment of the change's impact on the existing test bench
| Test strategy definition/review | Definition/review of test strategy (HW/FW/sequence)
| FTM Hw design | Test bench HW design (interfaces, instrumentation)
| FTM FW/ test sequence development | Machine FW and test sequence development
| Mechanical fixture design | Mechanical fixture design
| Component procurement | Procurement of components/materials
| Test machine / fixture manufacturing | Physical manufacturing of bench and fixture
| FTM Hw/Mechanical Assembly | HW and mechanical assembly on the bench
| FTM Hw-Sw Implementation | Integration and commissioning of FW on HW
| Internal validation | Internal validation (including backward compatibility)
| Factory Acceptance Test (FAT) & Release | Final acceptance test and bench release

## Organization DSM
ORGANIZATION-BASED DESIGN STRUCTURE MATRIX (DSM)
IHM convention: cell (row i, column j) is the weight of actor j's dependency on the output of actor i; the row actor provides a necessary input to the column actor.
Code | Organizational actor / role | Main responsibility | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
B1 | SCM & Product Engineering | Flags component obsolescence (EOL) | bar: B1 to B2
B2 | Product Owner | Opens the ECN and defines its priority | 3 | — | 2 | 2 | 2 | 2
B3 | R&D – HW Designer | Selects MCU-X and the programming connector; updates the electrical schematic | B2: 3; B3: —; B4: 1; B5: 1; B6: 1
B4 | R&D – Electronic Layout | Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10 | B2: 2; B3: 3; B4: —
B5 | R&D – FW Designer | Rewrites/adapts the DUT firmware for the new peripherals | B2: 2; B3: 3; B5: —
B6 | Test Engineering | Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates |  | 2 | 3 | 3 | 3 | — | 2 | 2 | 2
B7 | FTM Supplier – Firmware & Test Sequence | Updates the test-bench sequence and test firmware | B6: 3; B7: —; B8: 2
B8 | FTM Supplier – Test Machine Hardware | Adapts test-bench hardware, including programming interface and probes | B6: 3; B7: 1; B8: —
B9 | FTM Supplier – Mechanical Fixture | Adapts the mechanical fixture for probe access and component/board clearances | B6: 3; B9: —
LEGEND & ORGANIZATIONAL ELEMENTS
Weight | Dependency level | Interpretation | B2: Code; B3: Role; B4: English responsibility
0 / blank | No direct dependency | No direct input required from the row actor | B2: B1; B3: SCM & Product Engineering; B4: Flags component obsolescence (EOL)
1 | Weak / informal | Oral communication or e-mail; no tracked artifact | B2: B2; B3: Product Owner; B4: Opens the ECN and defines its priority
2 | Moderate / formal | Formal document, task, or coordinated deliverable | B2: B3; B3: R&D – HW Designer; B4: Selects MCU-X and the programming connector; updates the electrical schematic
3 | Strong / critical | Blocking input: recipient cannot proceed without it | B2: B4; B3: R&D – Electronic Layout; B4: Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10
— | Diagonal | Same organizational actor | B2: B5; B3: R&D – FW Designer; B4: Rewrites/adapts the DUT firmware for the new peripherals
|  |  |  | B6 | Test Engineering | Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates
|  |  |  | B7 | FTM – Firmware & Test Sequence | Updates the test-bench sequence and test firmware
|  |  |  | B8 | FTM – Test Machine Hardware | Adapts test-bench hardware, including programming interface and probes
|  |  |  | B9 | FTM – Mechanical Fixture | Adapts the mechanical fixture for probe access and component/board clearances

## Product-Process DMM
MULTI-DOMAIN MATRIX (MDM): PRODUCT × PROCESS
A filled cell means the product/system element is directly involved in the process activity.
Code | Product / system element | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
E1 | Microcontroller (MCU-X) | bar: P1 to P3; P7; P10 to P12
E2 | Programming connector | bar: P1 to P6; P9 to P12
E3 | Existing & new test points | bar: P1 to P4; P6 to P12
E4 | DUT firmware | bar: P1 to P12
E5 | FTM Measurement & Signal Conditioning Instrumentation | bar: P1 to P2; P7 to P8; P10 to P12
E6 | FTM-to-DUT Programming Interface | bar: P1 to P6; P9 to P12
E7 | FTM Fixture / Mechanical Interface | bar: P2 to P6; P9 to P12
E8 | FTM Electrical Test Interface | bar: P2 to P6; P9 to P12
E9 | FTM Fw & Test sequence | bar: P2; P7 to P8; P10 to P12
E10 | FTM Test Configuration | bar: P2; P8; P10 to P12
E11 | FTM Technical documentation | bar: P1 to P12

## Product-Organization DMM
MULTI-DOMAIN MATRIX (MDM): PRODUCT × ORGANIZATION
Filled cells indicate which organizational actors directly specify, design, communicate, modify, manufacture, integrate, validate, or document each product/system element.
Code | Product / system element | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
E1 | Microcontroller (MCU-X) | bar: B1 to B6
E2 | Programming connector | bar: B2 to B4; B6; B8 to B9
E3 | Existing & new test points | bar: B4; B6; B8 to B9
E4 | DUT firmware | bar: B2; B4 to B6; B8 to B9
E5 | FTM Measurement & Signal Conditioning Instrumentation | bar: B2 to B3; B5 to B7
E6 | FTM-to-DUT Programming Interface | bar: B2 to B4; B6; B8 to B9
E7 | FTM Fixture / Mechanical Interface | bar: B6; B8 to B9
E8 | FTM Electrical Test Interface | bar: B6; B8 to B9
E9 | FTM Fw & Test sequence | bar: B6 to B8
E10 | FTM Test Configuration | bar: B6 to B7
E11 | FTM Technical documentation | bar: B2 to B9

## Process-Organization DMM
MULTI-DOMAIN MATRIX (MDM): PROCESS × ORGANIZATION
Filled cells indicate which actors execute, provide required inputs to, coordinate, or validate each process activity.
Code | Process activity | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
P1 | Requirements / change analysis | bar: B1 to B6
P2 | FTM Impact assessment | bar: B2 to B6
P3 | Test strategy definition/review | bar: B3 to B4; B6; B8
P4 | FTM Hw design | bar: B4; B6; B9
P5 | FTM FW/ test sequence development | bar: B1 to B3; B6; B8 to B9
P6 | Mechanical fixture design | bar: B6; B8 to B9
P7 | Component procurement* | bar: B5 to B7
P8 | Test machine / fixture manufacturing | bar: B5 to B8
P9 | FTM Hw/Mechanical Assembly | bar: B6; B8 to B9
P10 | FTM Hw-Sw Implementation | bar: B5 to B9
P11 | Internal validation | bar: B6 to B9
P12 | Factory Acceptance Test (FAT) & Release | bar: B6 to B9