## Product DSM
PRODUCT DESIGN STRUCTURE MATRIX (DSM) — WITH INTERFACE TYPES
Cell notation = dependency strength · interface type. M = Mechanical · En = Energy · I = Information · Mat = Material
# | PRODUCT | E1 | E2 | E3 | E4 | E5 | E6 | E7 | E8 | E9 | E10 | E11
E1 | Microcontroller (MCU-X) | E1: *; E6: 3·M; E8: 2·M
E2 | Programming connector | E1: 1·En/I; E2: *; E6: 2·M; E7: 3·M; E8: 3·M
E3 | Existing test points (incl. TP3 – clock) | E1: 3·En/I; E3: *; E4: 1·M; E6: 2·M; E7: 2·M
E4 | New test points (TP9, TP10) | E1: 3·En/I; E3: 1·M/I; E4: *; E6: 3·M
E5 | DUT firmware | E1: 3·I; E4: 1·I; E5: *
E6 | PCB layout/pinout – DUT board, MCU area | E1: 3·M/En/I; E2: 2·M/En/I; E4: 2·I; E6: *; E7: 2·M; E8: 3·M
E7 | EOL test bench adapter electrical layout | E2: 3·M/En/I; E3: 2·En/I; E4: 3·En/I; E6: 2·M/En/I; E7: *; E8: 3·M
E8 | EOL test bench fixture (nest + pogo pins) | 2·M | 3·M/En/I | 2·M/En/I | 3·M/En/I |  | 3·M | 3·M/En/I | *
E9 | EOL test firmware | E1: 2·I; E4: 2·I; E5: 3·I; E9: *
E10 | FTM software | E4: 2·I; E5: 1·I; E9: 2·I; E10: *
E11 | Technical documentation | 2·I | 1·I | 1·I | 2·I | 1·I | 2·I | 1·I | 2·I | 1·I | 1·I | *
LEGEND
Dependency strength | Meaning | E2: Interface code; E3: Interface type; E4: Definition
1 | Weak — informational / low-risk dependency | E2: M; E3: Mechanical; E4: Geometry, fit, contact, alignment, mounting or physical constraint
2 | Medium — functional dependency requiring coordination | E2: En; E3: Energy; E4: Electrical power / voltage / current transfer
3 | Strong — structural / physical / constraining dependency | E2: I; E3: Information; E4: Signals, data, control, firmware/software or documentation
* | Diagonal — element itself | E2: Mat; E3: Material; E4: Transfer or flow of physical material; not materially present in this system
|  |  | M/En/I etc. | Mixed interface | More than one interface type acts across the same dependency

## Process DSM
PROCESS-BASED DESIGN STRUCTURE MATRIX (DSM)
Row = dependent activity · Column = activity on which it depends · Duration in weeks
# | Code | Process activity | Duration (weeks) | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
1 | P1 | Requirements / specifications receipt | 1 | bar: P1
2 | P2 | Test strategy definition | 1 | P1: 3; P2: •
3 | P3 | Electrical design of test machine / fixture | 3 | P2: 2; P3: •; P4: 3; P11: 3
4 | P4 | Mechanical fixture design | 3 | P2: 1; P3: 2; P4: •; P11: 3
5 | P5 | Component procurement* |  | P3: 3; P4: 2; P5: •
6 | P6 | Test machine / fixture manufacturing | 4 | P3: 2; P4: 3; P5: 3; P6: •; P10: 2
7 | P7 | Test firmware development | 3 | P2: 2; P3: 3; P7: •; P10: 3
8 | P8 | Test sequence development | 2 | P2: 2; P7: 3; P8: •; P10: 2
9 | P9 | Assembly | 2 | P5: 3; P6: 3; P9: •
10 | P10 | HW–SW integration | 2 | P7: 3; P8: 3; P9: 3; P10: •
11 | P11 | Internal validation | 3 | P10: 3; P11: •
12 | P12 | Factory Acceptance Test (FAT) | 1 | P11: 3; P12: •
|  | Total nominal process duration | 25 | P1: *Note: Component procurement is carried out concurrently with electrical and mechanical fixture design
LEGEND
Symbol / value | Meaning | Interpretation
• | Diagonal | Activity itself
1 | Weak dependency | Informational; low coordination / low risk
2 | Medium dependency | Functional; requires coordination
3 | Strong dependency | Structural / physical / constraining
Bold + red fill | Feedback marker | Dependency on a later activity; potential iteration / rework loop

## Organization DSM
ORGANIZATION-BASED DESIGN STRUCTURE MATRIX (DSM)
IHM convention: cell (row i, column j) is the weight of actor j's dependency on the output of actor i; the row actor provides a necessary input to the column actor.
Code | Organizational actor / role | Main responsibility | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
B1 | SCM & Product Engineering | Flags component obsolescence (EOL) | B1: —; B2: 3
B2 | Product Owner | Opens the ECN and defines its priority | B2: —; B3: 2; B4: 2; B5: 2; B6: 2
B3 | R&D – HW Designer | Selects MCU-X and the programming connector; updates the electrical schematic | B3: —; B4: 3; B5: 3; B6: 2
B4 | R&D – Electronic Layout | Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10 | B3: 1; B4: —; B5: 1; B6: 3
B5 | R&D – FW Designer | Rewrites/adapts the DUT firmware for the new peripherals | B3: 1; B5: —; B6: 2
B6 | Test Engineering | Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates | B6: —; B7: 2; B8: 2; B9: 3
B7 | FTM Supplier – Firmware & Test Sequence | Updates the test-bench sequence and test firmware | bar: B6 to B7
B8 | FTM Supplier – Test Machine Hardware | Adapts test-bench hardware, including programming interface and probes | B6: 1; B7: 3; B8: —
B9 | FTM Supplier – Mechanical Fixture | Adapts the mechanical fixture for probe access and component/board clearances | B6: 2; B8: 3; B9: —
LEGEND & ORGANIZATIONAL ELEMENTS
Weight | Dependency level | Interpretation | B2: Code; B3: Role; B4: English responsibility
0 / blank | No direct dependency | No direct input required from the row actor | B2: B1; B3: SCM & Product Engineering; B4: Flags component obsolescence (EOL)
1 | Weak / informal | Oral communication or e-mail; no tracked artifact | B2: B2; B3: Product Owner; B4: Opens the ECN and defines its priority
2 | Moderate / formal | Formal document, task, or coordinated deliverable | B2: B3; B3: R&D – HW Designer; B4: Selects MCU-X and the programming connector; updates the electrical schematic
3 | Strong / critical | Blocking input: recipient cannot proceed without it | B2: B4; B3: R&D – Electronic Layout; B4: Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10
— | Diagonal | Same organizational actor | B2: B5; B3: R&D – FW Designer; B4: Rewrites/adapts the DUT firmware for the new peripherals
|  |  |  | B6 | Test Engineering | Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates
|  |  |  | B7 | FTM – Firmware & Test Sequence | Updates the test-bench sequence and test firmware
|  |  |  | B8 | FTM – Test Machine Hardware | Adapts test-bench hardware, including programming interface and probes
|  |  |  | B9 | FTM – Mechanical Fixture | Adapts the mechanical fixture for probe access and component/board clearances

## Product-Process DMM
MULTI-DOMAIN MATRIX (MDM): PRODUCT × PROCESS
A filled cell means the product/system element is directly involved in the process activity.
Code | Product / system element | P1 | P2 | P3 | P4 | P5 | P6 | P7 | P8 | P9 | P10 | P11 | P12
E1 | Microcontroller (MCU-X) | bar: P1 to P3; P7; P10 to P12
E2 | Programming connector | bar: P1 to P6; P9 to P12
E3 | Existing test points (incl. TP3 – clock) | bar: P1 to P4; P6 to P12
E4 | New test points (TP9, TP10) | bar: P1 to P12
E5 | DUT firmware | bar: P1 to P2; P7 to P8; P10 to P12
E6 | PCB layout/pinout – DUT board, MCU area | bar: P1 to P6; P9 to P12
E7 | EOL test bench adapter electrical layout | bar: P2 to P6; P9 to P12
E8 | EOL test bench fixture (nest + pogo pins) – third-party manufacturer | bar: P2 to P6; P9 to P12
E9 | EOL test firmware | bar: P2; P7 to P8; P10 to P12
E10 | FTM software | bar: P2; P8; P10 to P12
E11 | Technical documentation | bar: P1 to P12
PROCESS ACTIVITY KEY
Code | English process activity | P1: Duration (weeks)
RS | Requirements / specifications receipt | bar: P1
DST | Test strategy definition | P1: 2
DE | Electrical design of test machine / fixture | P1: 3
DM | Mechanical fixture design | P1: 2
AC | Component procurement | P1: 3
RM | Test machine / fixture manufacturing | P1: 3
SFW | Test firmware development | P1: 3
SSQ | Test sequence development | P1: 2
ASM | Assembly | bar: P1
INT | HW–SW integration | P1: 2
VAL | Internal validation | bar: P1
FAT | Factory Acceptance Test (FAT) | bar: P1

## Product-Organization DMM
MULTI-DOMAIN MATRIX (MDM): PRODUCT × ORGANIZATION
Filled cells indicate which organizational actors directly specify, design, communicate, modify, manufacture, integrate, validate, or document each product/system element.
Code | Product / system element | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
E1 | Microcontroller (MCU-X) | bar: B1 to B6
E2 | Programming connector | bar: B2 to B4; B6; B8 to B9
E3 | Existing test points (incl. TP3 – clock) | bar: B4; B6; B8 to B9
E4 | New test points (TP9, TP10) | bar: B2; B4 to B6; B8 to B9
E5 | DUT firmware | bar: B2 to B3; B5 to B7
E6 | PCB layout/pinout – DUT board, MCU area | bar: B2 to B4; B6; B8 to B9
E7 | EOL test bench adapter electrical layout | bar: B6; B8 to B9
E8 | EOL test bench fixture (nest + pogo pins) – third-party manufacturer | bar: B6; B8 to B9
E9 | EOL test firmware | bar: B6 to B8
E10 | FTM software | bar: B6 to B7
E11 | Technical documentation | bar: B2 to B9
ORGANIZATION KEY
Code | Actor / role | B1: Responsibility
B1 | SCM & Product Engineering | B1: Flags component obsolescence (EOL)
B2 | Product Owner | B1: Opens the ECN and defines its priority
B3 | R&D – HW Designer | B1: Selects MCU-X and the programming connector; updates the electrical schematic
B4 | R&D – Electronic Layout | B1: Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10
B5 | R&D – FW Designer | B1: Rewrites/adapts the DUT firmware for the new peripherals
B6 | Test Engineering | B1: Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates
B7 | FTM – Firmware & Test Sequence | B1: Updates the test-bench sequence and test firmware
B8 | FTM – Test Machine Hardware | B1: Adapts test-bench hardware, including programming interface and probes
B9 | FTM – Mechanical Fixture | B1: Adapts the mechanical fixture for probe access and component/board clearances

## Process-Organization DMM
MULTI-DOMAIN MATRIX (MDM): PROCESS × ORGANIZATION
Filled cells indicate which actors execute, provide required inputs to, coordinate, or validate each process activity.
Code | Process activity | B1 | B2 | B3 | B4 | B5 | B6 | B7 | B8 | B9
P1 | Requirements / specifications receipt | bar: B1 to B6
P2 | Test strategy definition | bar: B2 to B6
P3 | Electrical design of test machine / fixture | bar: B3 to B4; B6; B8
P4 | Mechanical fixture design | bar: B4; B6; B9
P5 | Component procurement | bar: B1 to B3; B6; B8 to B9
P6 | Test machine / fixture manufacturing | bar: B6; B8 to B9
P7 | Test firmware development | bar: B5 to B7
P8 | Test sequence development | bar: B5 to B8
P9 | Assembly | bar: B6; B8 to B9
P10 | HW–SW integration | bar: B5 to B9
P11 | Internal validation | bar: B6 to B9
P12 | Factory Acceptance Test (FAT) | bar: B6 to B9
ORGANIZATION KEY
Code | Actor / role | B1: Responsibility
B1 | SCM & Product Engineering | B1: Flags component obsolescence (EOL)
B2 | Product Owner | B1: Opens the ECN and defines its priority
B3 | R&D – HW Designer | B1: Selects MCU-X and the programming connector; updates the electrical schematic
B4 | R&D – Electronic Layout | B1: Places the component, verifies pin-to-pin compatibility, and adds TP9/TP10
B5 | R&D – FW Designer | B1: Rewrites/adapts the DUT firmware for the new peripherals
B6 | Test Engineering | B1: Assesses test-bench impact, updates documentation, sends it to the manufacturer, and validates
B7 | FTM – Firmware & Test Sequence | B1: Updates the test-bench sequence and test firmware
B8 | FTM – Test Machine Hardware | B1: Adapts test-bench hardware, including programming interface and probes
B9 | FTM – Mechanical Fixture | B1: Adapts the mechanical fixture for probe access and component/board clearances